## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Time for type 7 Tasks
0 | 9/02/21 - 9/23/21 | Application chosen -> Trivia Application Technology stack chosen -> python/Flask decided all Essential and Non-Essential features | No implementation done, no issues | We decided who is doing what, other than that no issues | WIll decide upon iteration 1 | 0 | 0 | 0 | 0 | 0 | 114.5 | 92 | 22.5 | 34 | 20.5 | 3 | 2 | 3 | 9 | 9.5 | 11
1 | 9/24/21 - 10/23/21 | ESSENTIAL FEATURES Single Player Game LeaderBoard DESIERED FEATURES LifeLines - Skip Question in game timer | Team members were adding new feauteres old parts of the branch and pushing it to the head | -- | get all team members to be on different branches | 20 | 20 | 0 | 0 | 0 | 280 | 213.5 | 66.5 | 58 | 28.5 | 21 | 43.5 | 13.5 | 17.5 | 26.5 | 13.5
2 | 10/24/21 - 11/11/21 | Category Page Frontend/backend refactor Testing Framework Implemented User Login 50/50 lifeline |  |  |  | 9 | 9 | 5 | 2 | 3 | 278.5 | 185 | 93.5 | 48 | 68.5 | 56 | 37 | 70.5 | 25.5 | 26 | 28
3

## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unit test code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Daniel Makover | Drafted the Management Process Plan | Drafted the Single Player Story. Drafted alll chored related to code refactors | Drafter Sections on Software Design and UI |  | Iteration 0 - Created slides for management section Iteration 1 - Created Slides on Features and UI | Coded front end AJAX requests backend API endpoints and refactored Game Page |  | Deployed Code for both iteration 1 and iteration 2 to heroku | Managed the tasks among team members
Kun Mo | Discussed and Drafted the Management Plan together, updated the timeline in the Management Plan | Drafted "Start button", "Having questions", "Remaining time", "User main page" and "No duplicated questions Algorithm" user stories, filled some missing parts of other user stories | Drafted and updated No duplicated questions Algorithm in the section of key algorithm |  | Iteration 0 - Filled the slides of management plan Iteration 1 - Created and filled the slides of key algorithm | Iteration 1 - Contributed the front end and logic of Start button. Wrote the algorithm of no duplicated questions for the questions Iteration 2 - Contributed the front end and part of logic of Category page and contributed the front end and logic of main page | Iteration 1 - Wrote the informal testing codes for the algorithm of no duplicated questions |  |  | Created 10 movie type questions used in the game
Gunnar Nichols | Drafted and Managed the Quality Assurance Plan | Drafted the 'Quit Game' and 'Lifeline' User Stories (also part of lab2) | Updated the 'Security' section to reflect the transition to storing the game variables on the back end. | Drafted and managed the STD | Iteration0 - Created and Briefed QA Slide Iteration1 - Created and Briefed the 'Plans for Iteration2' Slide Iteration2 - Created the 'testing' slide and briefed it and the demo | Contributed on timer, random option location, Skip Question button, Score, UI and Question Cycling Moved all game variables and logic to backend, completed the implementation of the categories feature | Iteration 1 - Extensively manually the code and ensured that all primary game features were working properly Iteration 2 - Implemented the testing framework and organized the initial scope of our testing |  | Managed the team zoom | Came up with Game Title Created 10 questions used in the game
Heli Kolambekar | Drafted and Managed Sections: Overview, Related Work, and Proposed High Level Requirements , nonfunctional requirements | Drafted the FAQ and categories user stories. reviewed user stories of all members as requirement lead. | classes and methods' section and references |  | Iteration 0 - Created all slides related to Overview, Related Work, and Requirements Iteration 2- created and presented slides related to requirement analysis and refactoring | Iteration 0 - created Readme file Iteration 1- scorekeeping, lifeline functionalities Iteration 2- Categories page implementation | Iteration2- wrote unit test for the question table |  | took extensive meeting notes | added 20 questions to the questions database. created prototypes of all front end UI using Figma tool
Haoyi Zhu |  | Drafted the “One attempt each question” and "Show Remaining Lives" User Stories (also lab2) | Iteration 1 - Drafted the Software Architecture and Database Design Iteration 2 - Updated the Software Architecture and Database Design |  | Iteration0 - Created Framework Slides Iteration1 - Created 'Architecture' and 'DB design' slides Iteration 2 - Present for refactor | Iteration 1 - create function to check user selection matched answer or not. Create "Submit" and "Next" button, with logic. Create remaining lives function. Create function to show both correct and wrong answer when player submit their option. Edit display question, from a click function to an individual function. Merged most of the branchs. Iteration 2 - wrote 50/50 lifeline function, refactored game.js Submit function and DisplayNewQuestion function | Iteration 1 - manual testing for checking user selection function Iteration 2 - test 50/50 function followed the testing framework |  |  | Created 10 questions for the game
Weiye Xu | Drafted the Configuration and Management Plan | Drafted user stories that the user score show and the timer show in the UI, also need a login page for the gaame |  |  | Iteration0 - Created Configuration Plan Slides | Iteration 1 - Create the score function and the timer function, then merge to the iteration 1 |  |  |  | Created 10 questions for the game table
Yuwei Wu |  | Drafted the "player profile can view top scores" and "player profile can be edited and saved " user stories | Iteration 1 - security concerns and basic plan |  | Iteration0 - retouching slides iteration 1 - security concerns and plan iteration 2 - demo for player profile | iteration 1 - skip question button, a simple click counter for further score keeping feature iteration 2 - player profile page, view player score feature, editing and saving profile | Iteration 1 - manually test Iteration 2 - Feature test for player profile |  | meeting memo | Created 10 questions for the game

## Daniel Makover
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/12 | 12 | 9.5 | 2.5 | 0 - learn git and flask, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git | 6 | 2 |  |  |  | 0.5 | 1 |  | 1. Write section 4 of SPPP and Risk Mangement Spreadsheet 2. Participate in Iteration 0 presentation | 1. not familar with Flask framework 2. communication is not clear. Task assignments is not clear. | 1. finish Flask tutorial in 1 weeks, be able to create simple Flask hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Flask 1 - continue to define requirements 3 - implement a basic hello world on Flask | 9.5
2 | 09/13-09/19 | 17 | 14 | 3 | 0- Continue learning Flask 1-Finish risk management analysis and all iteration 0 documents 3-Created simple Flask App 6-Set up programing environement for Flask 7-Find and Analyse similiar projects from previouse groups | 5 | 4 |  | 2 |  |  | 1 | 2 | 1. Finished Risk Analysis 2. Finished Management Slides for presentation | 1. new to working with intergrating databases and authentication into a flask app | 1. Flask understanding is solid. Found a more advanced tutorial that covers topics that I am weak in. | 0- Learn db management and authenticaion with Flask 2- Desing the architecture for iteration 1 5- Make sure all coding components of Iteration 1 are assigned to appropriate team memebers | 10
3 | 09/20-09/26 | 8 | 8 | 13 | 0-Continue Learning Flask | 8 | [7 empty] | - | - | - |  | 10
4 | 09/27-10/03 | 0 | 0 | 0 | ABSENT(Wedding) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | - | - | - | - | 0
5 | 10/04-10/10 | 16 | 13 | 3 | 2-designed file structure and application layout 3-Created Boiler Plate code for front end ,backend, and database 5-documented newer version of README.md document 6- Set up virtual Environment | 0 | 1 | 7 | 0 | 0 | 2 | 3 | 0 | 1. Iteration 1 README.md file | 1. Not familiar with setting up virtual environment | 1. Found a number of tutorials for configuring virtual environments for python STATUS: DONE | 1- Configure correct environment for all team members | 10
6 | 10/11-10/17 | 13 | 10 | 3 | 3-Created CSV parser, front end AJAX functtionality 5-Delegated all Sprint tasks to team members 6- Configured all team members environement | 0 | 0 | 0 | 6 | 0 | 2 | 2 | 0 | 1.Updated Design Section of SDD | 1. Mac/Windows code combatibiltiy 2. varried knowledge level among team members | Iteration 1 was sucessfully completed | 1- Learn how to deploy to heroku | 10
7 | 10/18-10/24 | 12 | 10 | 2 | 6- Set up Deployment in Herkou | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Web App is Live | 1.no other team members learned this 2. had to learn how to migrate data | web app is now live | 1- Planing for iteration 2 | 10
8 | 10/25 - 10/31 | 9 | 7 | 2 | 0-Learning about Fflask Authentication and Authorization 3-Build proof of concept for flask authentication and authorization 5- Plan and delegate tasks for iteration 2 | 3 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | - | - | - | 1- Refactor code 2- add authentication feature | 10
9 | 11/1 - 11/7 | 12 | 10 | 2 | 0- learn Pytest 3- Refactor App and add authentication 5- Delegate other features and chored to teammembers | 3 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | - | - | - | 1- add features: Player profile 2-Add unit and feature tests | 10
10 | 11/8 - 11/14 | 14 | 12 | 2 | 0-Learn Pytest 3-Write unit and features tests for main, game, and leaderboard pages 6- Deploy to Heroku | 2 | 0 | 0 | 4 | 0 | 0 | 5 | 0 | 1.Updated project design section in SDD 2.added unit/feature tests 3. web app for iteration 2 is deployed | 1. coordinations will different branches is getting very complicated | 1. Will need to have better branch orginization for iteration 3 | 1- Planning for iteration 3 | 10

## Heli Kolambekar
The example shows below. Only include the time that you use to work on the project.
Lead Roles: requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/10-09/16 | 8 | 7 | 1 | 0 - learn git, flask, understand SE project development principles 1 - built consensus on the essential, desirable and optional features. Came up with the security and non functional requirements after surveying other trivia apps 5 - communicated with team members to finalize product functional requirements 6 - set up github, pivotal tracker 7 - research similar products, prepare presentation | 2.5 | 3 |  |  |  | 0.5 | 0.5 | 0.5 | 1. set up github, pivotal tracker 2. draft project description in Google Drive folder 3. survey other trivia applications | 1.lack of familiarity with SE tools 2. difficulty setting achievable requirement product goals 3. incompleteknowledge of SE project development principles | 1. try flask and javascript hands-on 2. research product features of different webapps 3. search for quiz datasets of varioud categories | 0. finalize product requirements 1. work on SPPP 2. work on project structure and implementation 3. implement a basic program using flask | 9
2 | 09/17-09/23 | 10 | 8 | 2 | 0- learn javascript, pivotal tracker work hands on with flask 1- compare features of other trivia apps, draft the project functional , security , non-functional requirements in Project_SPPP and Iteration0 ppt 5- draft and commit the Readme file 6- set up all programs for project dependencies 7- review projects from previous semesters | 3 | 2.5 |  |  |  | 1 | 0.5 | 1 | 1. Draft Section 1,2,3 of SPPP detailing overview, related work and high level requirements 2. draft and commit Readme file on github detailing project description 3. drafted ppt slides for introducti on, project features | 1. unfamiliar with flask software development environment 2. challenge to evaluate preexisting projects | 1. worked on flask 2. looked for implementation ideas for the project | 1. create implementation plans for next week 2. create pivotal tracker stories to coordinate efforts | 8
3 | 09/24-09/30 | 8 | 6.5 | 1.5 | 0- continue learning javascript 1- wrote 2 completed user stories using Pivotal Tracker with acceptance tests 2- design the lifelines for gameplay 7- search for question bank databases | 2 | 2 | 1 |  |  |  |  | 1.5 | meeting minutes | 1. limited experience with javascript 2. limited experience with pivotal tracker | 1. continue growing javascript knowledge find easier way to load questions to database | 1. create prototypes of front end UI | 8
4 | 10/01-10/07 | 8.5 | 7 | 1.5 | 0-continue to learn Javascript. SQLite 1- created mockups of all webpages using front end prototyping tool called Figma. Created class diagram for the play page using lucidchart | 2 | 5 | [6 empty] | meeting memos prototypes of all front end UI using tool called figma | 1. learning new tool called figma, used for front end prototyping | 1. continue working with java script. 2. create question categories | test functionalities of game and start imple mentation | 8
5 | 10/08-10/14 | 8.5 | 6 | 2.5 | 0- learn jquery 1- create 10 questions for 'TV show' category for the database 2- design the lifelines and scoring on play page 4- test the working functionalities of the game | 2 | 1 | 1 |  | 2 |  |  |  |  | 1. difficulty running jquery commands 2. difficulty in resolving merging conflicts | 1. understanding merging conflict resolution | use interdependent functionalities for creating user functions | 9
6 | 10/15-10/21 | 9.5 | 7 | 2.5 | 0- continue learning jquery 3- scorekeeping and lifelines functions 4- test and run the game on local machine | 2 | 4 | 1 | [5 empty] | 1. SDD, SPPP revisions 2. project presentation slides 3. meeting memo | 1. difficulty in comprehen ding comitted code | 1. asking for clarification from team members regarding code snippets and variable naming | project presentation and demonstration | 10
7 | 10/22-10/28 | 8 | 6 | 2 | 0- learn AJAX, continue learning JS 7- make improvements based on feedback from instructor for Iteration-1 | 4 | [6 empty] | 2 | 1. revising the SPP, SDD based on feedback from instructor after Iteration 1 | 1. understanding AJAX requests | looking up tutorials and other materials online to remove confusion | create mockups for the pages in the next iteration | 8
8 | 10/29-11/4 | 9 | 7 | 2 | 0- understand refactoring and learn refactoring techniques. watch tutorial on creating user authentication 1- create mockups for player profile, login and categories pageusing tool called Figma add new user feature stories on Pivotal Tracker | 2 | 5 | [6 empty] | 1. meeting memo | 1. understanding refactori ng techniques and imple- mentation | 1. learning from appropriate sources about refactoring | work on categories user stories write test code | 8
9 | 11/4-11/11 | 14 | 10 | 4 | 0- learn about code smells and ways to improve code readability 3- design the categories page, refactor a portion of the code which creates a function to add score to leaderboard. 4- write functional tests to test the Question table using pytest | 2 | 6 |  | 2 |  |  |  |  | meeting memo updated SDD, SPP ppt sections- benefits of refactoring and plans for Iteration-3 | 1. difficulties pulling questions of a particular category on the categories page | collaborating with other members to find a solution |  | 8

## Haoyi Zhu
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/12 | 6 | 5 | 1 | 0 - learn flask and MongoDB (get basic idea) 1 - review other groups projects on GitHub 2 - search data about our trivia app questions 3 - 4 - 5 - edit part of week1 meeting note before the meeting, set up meeting purpose 6 - 7 - research similar project | 1.5 | 1 | 1 |  |  | 0.5 |  | 1 | N/A | 1. not familar with flask framework and MongoDB | 1. finish flask and MongoDB tutorial in 3 weeks, be able to create a sample by using flask next week | 0 - continue to learn flask and MongoDB 1 - implement a basic sample on flask 2 - try to connect a sample project with MongoDB | 6
2 | 9/13-9/19 | 9.5 | 6.5 | 3 | 0 - keep learn flask 1 - edit framework part PowerPoint preparation 2 - 3 - 4 - 5 - 6 - finished a sample project with flask, but not yet connect with database 7 - research more trivia game for software development design(mostly front end) | 2 | 1 |  |  |  |  | 2 | 1.5 | Finished framework part PowerPoint for iteration 0 preparation | 1. didn't have enough time to do more for the sample 2. 3. | give more time for learning | 1. continue to learn flask, try put more time on it 2. start working on software design plan 3. | 8
3 | 9/20-9/26 | 6 | 4 | 2 | 0 - Learn HTML, CSS, JavaScript 1 - 2 - Draw ERD for database design 3 - 4 - 5 - 6 - 7 - | 3 |  | 1 | [5 empty] | N/A | Logic issue with design database, how to connect question table with others | Plan to restructure the ERD | Keep learning JS and working on the userstory | 6
4 | 9/27-10/3 | 6.5 | 4.5 | 2 | 0 - Keep learn JavaScript, learn JQuery 1 - Looking for document how to write SDD, Working on userstory 2 - 3 - 4 - 5 - 6 - 7 - | 3 | 1.5 | [6 empty] | Provide ERD for database design. Added two userstories for our project |  |  |  | 10
5 | 10/4-10/10 | 11 | 8 | 3 | 0 - Learn how to use all tool toghter 1 - Add tasks to userstory 2 - Draw Software Architecture MVC view 3 - write 10 questions for our game 4 - 5 - Join front end meeting 6 - 7 - | 5 | 1 | 0.5 | 0.5 |  | 1 |  |  | Provide 10 questions for database. Added tasks for two userstories |  |  |  | 20
6 | 10/11-10/17 | 33.5 | 30.5 | 3 | 0 - Learn JQuery 1 - Provide requirement for function updat 2 - 3 - Coding: create function to check user selection matched answer or not. Create "Submit" and "Next" button, with logic. Create remaining lives function. Create function to show both correct and wrong answer when player submit their option. Edit display question, from a click function to an individual function. Debug 4 - Manually test whether the function is working properly with my own function and each merge. 5 - Discusses with Gunnar with randomize question function. Ask group member provide comments for their coding. Provide requirement for function update to groupmember. 6 - 7 - Merge all group members branch to iter_1 branch | 4 | 0.5 |  | 17 | 2 | 1 |  | 6 | Finished all the functional coding. Merged all group members branch to iter_1. |  |  |  | 10
7 | 10/18-10/24 | 5 | 3 | 2 | 0 - 1 - Drafted Software Architecture and Database Design for SDD, working on presentation for these two part 2 - 3 - 4 - 5 - merge iter_1 branch to main branch 6 - 7 - |  | 3 | [6 empty] | Drafted Software Architecture and Database Design for SDD, merged main branch |  |  | Learn the skills needed for the next iteration | 2
8 | 10/25 - 10/31 | 4 | 2 | 2 | 0 - Learn Flask blueprint 1 - 2 - 3 - 4 - 5 - 6 - 7 - | 2 | [7 empty] | Learn |  |  | 1.write the new function required 2.refactor code | 4
9 | 11/01 - 11/07 | 9.5 | 7.5 | 2 | 0 - learning pytest 1 - 2 - 3 - Working on 50/50 lifeline function, refactor game.js, and debug 4 - 5 - 6 - 7 - | 0.5 |  |  | 7 |  |  |  |  | Wrote 50/50 lifeline function, refactored game.js Submit function and DisplayNewQuestion function | Something went wrong with my push at Sunday. A variable which is using for 50/50 function is not global variable. This issue cause submit, next question, and skip question function not working | Rolling back all my update at Gunnar's branch, created another individual branch for saving the code. Debuged on Sunday, soved the issue | keep learn pytest, and test 50/50 function | 2
10 | 11/08 - 11/14 | 8 | 5.5 | 2.5 | 0 - keep learning pytest 1 - Update Software Architecture and Database Design for SDD, prepare for the iteration 2 presentation 2 - 3 - 4 - use pytest to test 50/50 function 5 - Discuss with Kun how to implement category function 6 - 7 - | 1 | 2 |  |  | 0.5 | 2
11
12
13
14
15
16
17
18
19

## Kun Mo
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 9 | 7 | 2 | 0 - Learn git and django, read several tutorials 1 - Discussed high level requirements, drafted the management plan of SPPP together 5 - Send reminders to team members 6 - Set up git 7 - Research similar products and showed them to the team members, prepare presentation | 3 | 2 |  |  |  | 0.5 | 1 | 0.5 | 1. Set up git, commit personal intro and merge the team member intro on github 2. Participate in Iteration 0 presentation | 1. Not familar with flask framework 2. Hard to make a decision for the meeting date | 1. Keep learning, be able to create simple hello world project next week. 2. Spend more time to discuss the meeting date, using free time to push the decision on slack. | 0 - Continue to learn flask 1 - Continue to discuss requirements 3 - Implement a basic hello world on flask | 9
2 | 09/13-09/23 | 10.5 | 7.5 | 3 | 0 - Keep learning flask 1 - Add some stuff for the risk management, make a risk distribution diagram for the presentation, fill the slides of management plan of our presentation 5 - Assign the tasks of iteration 0 for each team members, send reminders to team members, look over the team works 6 - Set up the programming environment of flask | 2 | 3 |  |  |  | 1.5 | 1 |  | 1. Discussed and drafted the management plan of SPPP together 2. Filled the iteration 0 presentation slides of management plan | 1. Hard to show all the risks in risk management in one page slides. 2. We found some roles in the project is not obvious so the people of that roles will have less contribution. | 1. Make a risk distribution diagram that contain all the risks, and just explain the top 3 risks. 2. Every member can join in to the works of developer, designer and tester. Everyone can have 2 or even 2 more roles. | 0 - Continue to learn flask 1 - Update SPPP and SDD, participate in Iteration 1 presentation, write user stories 2 - Start the design of our project 6 - Understand how to make a new version in github | 7
3 | 09/23-09/30 | 5.5 | 3.5 | 2 | 0 - Learned html 1 - Wrote 2 completed user stories of KnowItAll with tasks and test acceptances on pivotal tracker 5 - Delegated the tasks of SDD for each memebers | 1 | 1.5 |  |  |  |  | 1 |  | 1. Wrote 2 completed user stories of KnowItAll with tasks and test acceptances on pivotal tracker | 1. Did not clearly understand what tasks and test acceptances need to be written on | 1. Go over the requirements and objectives from the documents we currently have | 0 - Keep learning html, javascript and css 1 - Keep writing the user stories on pivotal tracker 2- Design class diagram 3 - Start writing html codes | 9
4 | 09/30-10/07 | 11.5 | 9 | 2.5 | 0 - Learned javascript, html and css 1 - Add more user stories for iteration 1 at pivotal tracker 2 - Made the sample UML class diagram for our project 3 - Wrote the html and css codes of play page 5 - Follow-up the html codes of developers 6 - Checked the environment for html | 2 | 1 | 2.5 | 2 |  | 1 | 0.5 |  | 1. Add more user stories for iteration 1 at pivotal tracker | 1. Could have some users stories of iteration 1 still not contain in the pivotal tracker | 1. Follow the progress of iteration 1 implements to complete and add more user stories | 0 - Keep learning html 1 - Keep writing the user stories on pivotal tracker, and finish them in iteration 1 3 - Keep writing the codes we need 6 - Set up the environment/commands of dataset | 9.5
5 | 10/07-10/14 | 14 | 11.5 | 2.5 | 0 - Keeped learning javascript, html and css 1 - Wrote 10 movie type questions for our dataset of trivial game, added some user stories for iteration 1 of project and finish their tasks and test acceptances 3 - Created the play game button on the play page and write its logical codes, make a logic for the requirement of no duplicated questions 4 - Test the start game button and make sure the button is working 6 - Setted up the environment of flask and the commands of uploading the dataset to flask | 2 | 4 |  | 4 | 0.5 |  | 1 |  | 1. Add 10 questions about movie to our dataset of trivial game 2. Finished adding and filling the user stories, including their tasks and test acceptances 3. Wrote and tested the play game button on the html of play page | 1. the querySelector can only select the first element within the html that matches the selector | 1. Wrote a for loop function to let the querySelector to go over and select all html contents that mathes the selector | 0 - Continue learning html, javascript and css 1 - Make iteration 1 presentation slides and prepare for the presention 3 - Continue writing the codes | 9
6 | 10/14-10/21 | 11.5 | 10 | 1.5 | 0 - Keep learning html 1 - Explain the logic of no duplicated questions on the key algorithm in SDD, fill in the key algorithm part of iteration 2 presentation slides 2 - Make an algorithm diagram of no duplicated questions 3 - Write the new logic codes for no duplicated questions 4 - Test and make sure the logic codes work well | 2 | 3 | 1 | 2 | 2 |  |  |  | 1. Wrote a better logic for no duplicated questions in application, and pass the test 2. Wrote the logic of no duplicated questions under the part of key algorithm of SDD | 1. For the old logic of no duplicated questions, as more and more id has been used, the comparison of question id in system will be increasing, the probability of "failed to use" question id will be also increasing, the execution efficiency is low. | 1. Rewrote a new logic that the system just randomly pick the question id from rest id, it wouldn't ever fail to find and use the question id. | 0 - Continue learning html, javascript and css 1 - Discuss about the iteration 2 requirements 7 - Prepare for the presentation of iteration 1 | 6
7 | 10/21-10/28 | 5.5 | 3.5 | 2 | 0 - Keep learning flask 1 - Updated risk management part of SPPP, and added the explanation of the number in the risk matrix and showed the top 3 risks 5 - Made a release for the github codes and submit all the files to blackboard | 1.5 | 1.5 |  |  |  | 0.5 |  |  | 1. Made a release for the github codes and submit all the files to blackboard 2. Added more contents on risk management of SPPP 3. Participate in Iteration 1 presentation |  |  | 0 - Continue learning flask and html 3 - Start coding for iteration 2 requirements 5 - Delegate the works for every members | 8
8 | 10/28-11/04 | 6.5 | 4.5 | 2 | 0 - Keep learning html 3 - Write html codes with mouse movement function for the main page 7 - Create two bug report on github | 1.5 |  |  | 2 |  |  |  | 1 | 1. Wrote the main page html for our trivial game |  |  | 0 - Continue learning html, javascript and css 1 - Keep coding for the iteration 2 requirements 7 - Prepare for the presentation of iteration 2 | 9
9 | 11/04-11/11 | 15.5 | 12.5 | 3 | 0 - Keep learning html and flask 3 - Rewrite some codes on category page to make them more concise and clean, write uncompleted logic of select category, fix the bug of "Clickable category text issues" and write logic to slove the bug of "Remember the category selection forever", update the timeline in SPPP, update the description of key algorithm of SDD 4 - Write testing for category (unfinished) 5 - Follow-up the works this week and delegate the rest works to each team members | 3.5 |  |  | 6 | 1 | 2 |  |  | 1. Rewrote and clean up the html of category page for our trivial game 2. Fixed some posting bugs on github 3. Updated the timeline in SPPP 4. Updated the description of key algorithm of SDD | 1. Having some unknown issues in the passing process of click button action from html to category.py. 2. The category page will remember the selection forever when the player has been selected the category, even they quit the game and did not select any category in the second game play. | 1. Asking other team member for help and found the issues that category.py wasn't registering with our program because it wasn't initialized in the init file 2. Adding some logic to make "all" selection of category cover the older selection for each category page loading. Then the game page will always automatically load all the questions for the player, until the player select category. | 0 - Continue learning html, javascript and css 1 - Discuss about the iteration 3 requirements 3 - Start coding for iteration 3 requirements 5 - Delegate the works for every members | 7
10 | 11/11-11/18 | 0 | 0
11 | 11/18-11/25 | 0 | 0

## Yuwei Wu
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 2.5 | 2.5 |  | 0 - class material familiarizing 5 - meetings/discussions 7 - brainstorming feasible project(s) | 0.5 |  |  |  |  | 1 |  | 1
2 | 9/14-9/23 | 3 | 3 |  | 0 - class material familiarizing, flask familiarizing 5 - meetings/discussions | 1 |  |  |  |  | 2
3 | 9/24-9/30 | 3 | 3 |  | 0 - learning 5 - meetings/discussions | 0.5 |  |  |  |  | 2.5 |  |  | 1- research about security concerns
4 | 10/1-10/7 | 5.5 | 5.5 |  | 0 - learning 2 - design 5 - meetings/discussions | 1 |  | 2 |  |  | 2.5 |  |  | 0 - learning html 2 - player profile basic html page design 2 - user stories
5 | 10/8-10/14 | 9 | 9 |  | 0 - learning 2 - design 4 - test 5 - meetings/discussions 6 - configuration/environment 7 - unclassified | 2.5 |  |  |  | 0.5 | 3.5 | 1.5 | 1 | 0 - learning how to implement environment 0 - learning how to use pycharm for the project 2 - skip button, counting correct question 4 - test the buttons in 2 6 - set the environment and update recent pushes 7 - sdd security part outlining 7 - 10 questions in art category
6 | 10/15-10/21 | 4 | 4 |  | 0 - learning 5 - meetings/discussions 7 - unclassified | 1 |  |  |  |  | 1.5 |  | 1.5 | 0 - research about the security needs and solutions 7 - sdd & relevant part of the slides
7 | 10/22-10/28 | 1.5 | 0.5 | 1 | 2 - design 5 - meetings/discussions |  |  | 0.5 |  |  | 1 |  |  | 2 - player profile design
8 | 10/29-11/5 | 2.5 | 1.5 | 1 | 0 - learning 5 - meetings/discussions 7 - unclassified | 1 |  |  |  |  | 1 |  | 0.5 | 0 - user authentication case/example learning 7 - 10 questions in art category
9 | 11/6-11/11 | 12 | 9 | 3 | 0 - learning 2 - design 4 - test 5 - meetings/discussions 6 - configuration/environment | 3 |  | 1 |  | 2 | 3 | 3 |  | 0 - learning about test doc 2 - designing and optimizing the player profile page 4 - test: write test doc for player profile page 5 - meetings/discussions 6 - config env | some issues about the environment

## Gunnar Nichols
Lead Roles: Quality Assurance Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/10-09/16 | 7 | 6 | 1 | 0 - Read about flask and understand how it is utilized - 1 1 - Review all previous project submissions and projects of similar scope online - 2 2 - Look up trivia web apps currently usable online - 1.5 7 - Review all requirements for Iteration 0 - 1 7 - Set up group zoom account - 0.5 | 1 | 2 | 1.5 |  |  |  |  | 1.5 | N/A | (a) Lack familiarity of utilizing many of the programming tools together | (a) Will create a simple program which uses the same programming tools to gain an understanding of how they work together by the end of Iteration 0 | 0 - Review JS/Python, MangoDB - 1.5 2/3 - Think of project's structure and implementation - 1 4 - View examples and draft Draft QA Section of SPPP - 2 6 - Set up all programs for project dependancies - 2 7 -Look up comparable programs - 1 | 7.5
2 | 09/17-09/23 | 10.5 | 8.5 | 2 | 0 - Review previous references for JS/Python - 1, Put together a simple Flask Project and review Documentation - 1.5 2 - Review example of another individuals implementation of a trivia webapp - 0.5 4 - Review Previous Groups SPPP and Draft the QA Plan as well as QA Slides for Iteration0 Presentation - 3 6 - Set up all programs for project dependancies on my personal laptop - 1.5 7 - Review all quality trivia games accessable from google's first page -1 | 2.5 |  | 0.5 |  | 3 |  | 1.5 | 1 | Drafted QA Plan for SPPP and QA Plan Slides for Iteration 0 Presentation |  | (a) I have completed a simple project which used Python/Flask, but I still need to understand MangoDB more. I am not very worried about this though. | 0 - Watch Flask Tutortial Video and make the simple blogging website example - 3.5 2 - Draft initial notes on how it seems like we should want to implement specific features - 1.5 7 - Organize all required work for Iteration 1 - 1 | 6
3 | 09/24-9/30 | 8.5 | 7 | 1.5 | 0 - Watch Flask Tutorial and Completed simple blogging website with CRUD functionality 2 - Drafted notes on how certain features could be implemented based on what I learned from the Flask Tutorial - 1 4 - Research Pytest and watch tutorials - 1.5 7 - Understand the scope of the work which the group needs to complete for the end of Iteration 1 - 1 | 3.5 |  | 1 |  | 1.5 |  |  | 1 | N/A |  | (a) We have decided we will likely be using sqllite with I am comfortable with so now that I have worked with flask and built simple webapplications which are slightly smaller in scope than the project we're working on I am comfortable with everything I expect to have to do programing wise. I still need to prepare the testing details. | 0 - Review html/css/jquery - 2. 2 - Build a sample version of our application to get an idea how to implement anything I am required to - 3. 7 - Review previous groups SDD to have a standard of what a good SDD will look like - 1 | 6
4 | 10/01-10/07 | 7.5 | 6 | 1.5 | 0 - Review html/css/jquery - 2 2 - Created a personal simplified version of our game to get an idea for how I would need to implement anything I was required to - 3 7 - Review previous groups SDDs - 1 | 2 |  | 3 |  |  |  |  | 1 | N/A |  |  | 0 - Review github functionality and how to properly manage and merge a branch/branches - 1.5 3 - Create functionality for the 4 options to appear in a random location - 1 4 - Test the nearly finished game and establish improvements to be made for the end of the iteration - 3 7 - Write 10 questions to be used in the game - 1 | 6.5
5 | 10/08-10/14 | 9.5 | 7 | 2.5 | 0 - learn github slightly better than was done in the lab - 2 3 - Create option randomization functionality - 1 4 - Test the nearly finished game - 3 7 - Write 10 questions for the game | 2 |  |  | 1 | 3 |  |  | 1 | Wrote 10 questions to be used in the game Created functionality to let the 4 options appear in a random location |  |  | 0 - Learn how to accomplish anything I can't figure out while programming - 2 3 - Complete tasks assigned to complete the working product for iteration 1 - 3 4 - Re-Test the finished game and fix all remaining devient behavior. - 2 | 7
6 | 10/15-10/21 | 11.5 | 9 | 2.5 | 0 - Learned how Ajax works, continued to review js and html documentation as needed, looked into code in the program I didn't understand - 3 2 - Designed the plan for resuming a game instance after the user functionality is added - 1 3 - Completed properly implementing the timer, time based scoring, question cycling, and misc minor improvements - 3 4 - Tested the games 'edge case' behavior for all critical game features and verified everything was working as intended - 2 | 3 |  | 1 | 3 | 2 |  |  |  | Fixed the Timer Implemented Time Based Scoring Added Question Cycling Final Unit Testing on Iteration 1 Product Drafted 'Iteration 2 Plans' Slide for Iteration 1 Presentation | (b) I have not had many issues | (b) I do not believe this is a significant issue, but if it is I will outline whenever I have to learn something new, even if that never takes long. | 2 - Organize Refactoring Plan - 1.5 | 5.5
7 | 10/22-10/28 | 6 | 4 | 2 | 0 - Review pytest documentation 2hr 2 - Planned the score of the variable transition to the backend - 2hr | 2 |  | 2 | [5 empty] | N/A |  |  | 0 - Learn how the user code works - 2 3 - Rewrite the game variable refactor code - 6 | 8
8 | 10/29-11/4 | 14 | 12 | 2 | 0 - Specific details of getting our code to work (flask)- 2 3 - Refactor the game variables to backend - 8 4 - Manual Testing of game refactor - 2 | 2 |  |  | 8 | 2 |  |  |  | Move game variables to backend and simulated all game logic in url calls. | (c) I had the entire transition of the backend code organized but when attempting to see if the idea would work I ran into the issue that the information wasn't getting to the frontend before the variables were being used by the frontend. | (c) Ajax requests are asynchronous by default. This was solved by setting async: false, inside the ajax request. | 4 - Establish the baseline test framework for our program and implement simple tests. Help Each individual figure out a test for their lab. 4 7 - Prepare for iteration 2 presentation - 1 | 5
9 | 11/4-11/11 | 15 | 11 | 4 | 0 - Specific details of getting our code to work (jQuery) - 2 3 - Get the category feature working (unplanned) - 4 4 - Implement Testing Framework and draft initial tests/STD - 3 7 - Draft Demo/Testing portion of the presentation - 1 | 2 |  |  | 4 | 4 |  |  | 1 | Implemented the testing framework Drafted the STD Completed implementation of 'Category' feature | (d) it took a very large amount of my time to do all of the things required to get the project in a state that I was comfortable with for the end of iteration 2 | (d) I plan on expecting to accomplish less in the next iteration and to really refine what we already have so I do not have to personally implement many more things. | 4- Continue to improve the automated testing - 3 | 3
10 | 11/12-11/18 |  |  |  | 0 - 1 - 2 - 3 - 4 - 5 - 6 - 7 -
11 | 11/19-11/25 |  |  |  | 0 - 1 - 2 - 3 - 4 - 5 - 6 - 7 -
12 | 11/26-12/02 |  |  |  | 0 - 1 - 2 - 3 - 4 - 5 - 6 - 7 -
13 | 12/03-12/09 |  |  |  | 0 - 1 - 2 - 3 - 4 - 5 - 6 - 7 -
14 | 12/10-12/16 |  |  |  | 0 - 1 - 2 - 3 - 4 - 5 - 6 - 7 -

## Weiye Xu
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/12 | 4.5 | 3.5 | 1 | 0 - learn git 5 - meeting with team member though zoom 6 - set up git | 2 |  |  |  |  | 0.5 | 1 |  | 2. Set up git, commit a the assignment1 to test on git | 1. communication is not clear |  | 0 - continuing to learn git 1 - continue to define requirements | 6
2 | 09/13-09/19 | 5 | 4 | 1 | 0 - learn git and flask 5 - edit the comfigurant part in the SPPP file - group meeting and discussion 7 - prepare the iteration 0 presentation | 2 |  |  |  |  | 1 |  | 1 | 1. Write the comfiguration section of SPPP | 1. not familiar with the flask framework 2. configuration part in SPPP file still not clear. | 1. finish the flask turtorila in this week, able sto create some simple project. | 0 - continuing to learn Git and Flask | 8
3 | 09/20 - 09/26 | 5 | 4 | 1 | 0 - learn git and flask 7 - complete pivotaltracker and user story | 2 | [6 empty] | 2 | 1.Write the user stories in the pivotaltracker | 1. not spefic some detail tasks for some user stories. 2. not able to clone the git repository though the SSH issues. | 1. creating detail task of user stores, 2. Fixing the problem and reconnect with the git repository. | 0 - continusing to lean Git and Flask | 6
4 | 09/27 - 10/03 | 5 | 2 | 3 | 0 - learn git and flask | 2 | [7 empty] | N/A
5 | 10/04 - 10/10 | 7 | 4 | 3 | 0 - learning git, html and javascriptx 3 - implementating Timer function, and score calculate function | 1 |  |  | 3 |  |  |  |  | 1. Create 10 questions to the data bases 2. Finish Timer function, and score calculate function | 1. Timer function need to be update base on the new UI. 2. Score Calculate need to be specific the score, right now, only count the number of correct answer | 1. need the timer start timing after the start button click, and stop when click the submit button 2. timer function new feature: 1. when timer is finish, automative submit the answer, and reset the timer when go to the next question. | 0 - continusing to lean Git and Flask, html, and javascript 3 - Finish the implementation of the new feature. | 2
6 | 10/11 - 10/17 | 4.5 | 3 | 1.5 | 0 - learning git, html and javascriptx 3 - Timer function fixed and update | 1 |  |  | 2 |  |  |  |  | 1. merge the fixed timer function to the iteration 1 |  |  | 0 - continusing to lean Git and Flask, html, and javascript | 1
7 | 10/18 - 10/24 | 2 | 0.5 | 1.5 | 7 - Prepare the iteration 1 | [7 empty] | 0.5 |  | 1. Since there are too much works from other course, does not participate lot of work in this week |  | 0 - continusing to lean Git and Flask, html, and javascript | 1
8 | 10/25 - 10/31 | 8 | 6 | 2 | 0 - learning implmenting the login, logout and signup funtion 3 - Implementing the login, logout and sign up function | 3 |  |  | 3 |  |  |  |  | 1. Create a signup funtion and player table modules database to to store player info. |  |  | 4 - unit test or pytest implementation 4 - Bugfix and Code Refactor
9 | 11/01 - 11/07 | 10 | 7 | 3 | 0 - learning implmenting the login, logout and signup funtion 1 - learning and analysis the unittest and pytest 3 - Implementing the login, logout and sign up function 4 - Test and fixed some issues. | 1 | 2 |  | 3 | 1 |  |  |  | 1. Login, Logout and sign up function. | 1. CSS style does not work, bootstrap cdn issues 2. player profile does not link to the player account, and still ask player's name after login. | 1. change to the bootstrap cdn instead using the local file 2. Fix the bug with the player profile and player account connection issue. | 4 - unit test or pytest implementation 5. Fix the bug with the player profile and player account connection issue.
10 | 11/08 - 11/14 | 3 | 0 | 3 | 4 - try to write the pytest for testing router and model 7 - Prepare the iteration 2 | [11 empty] | 3 - Player profile management and super User Create.